## Sprint 1
Sprint 1 - 11/1/23 to 11/10/23
User Story | Story Point | Assigned To | Cumulative Hours
Frontend Tool Research | 4 | Surya | 16
Backend / AI Research | 4 | Jayani | 16
Database | 4 | Raksha | 16
Management tool Research | 4 | Pallavi | 16

## Sprint 2
Sprint 2 - 10/27/23 to 11/10/23
User Story | Story point | Assigned To | Cumulative Hours
Create Database | 4 | Jayani | 16
Create API Flask | 4 | Raksha | 16
Integraytion database to API | 4 | Surya | 16
Jira Tool setup / Documentation | 4 | Pallavi | 16

## Sprint 3
Sprint 3 - 11/10/23 to 11/20/23
User Story | Story Point | Frontend | Backend | Management/Documentation | Cumulative Hours
Search Initiation | 3 | Surya | Raksha, Jayani | Pallavi | 12
Landing Page | 5 | Surya | Raksha, Jayani | Pallavi | 16
Search Recommender | 3 | Surya | Raksha, Jayani | Pallavi | 16
User Login - Existing User | 5 | Surya | Raksha, Jayani | Pallavi | 12
User Login - New User | 5 | Surya | Raksha, Jayani | Pallavi | 16
Search Visualization | 3 | Surya | Raksha, Jayani | Pallavi | 12

## Sprint 4
Sprint 4 - 11/20/23 to 12/5/23
User Story | StoryPoint | Frontend | Backend | Management/Documentation | Cumulative Hours
Frontend Interaction | 3 | Surya, Jayani | Raksha | Pallavi | 12
Redirect to Login Page | 5 | Surya, Jayani | Raksha | Pallavi | 18
Document Ranking - NLP task | 8 | Surya, Jayani | Raksha | Pallavi | 24
View Article from the list of articles | 8 | Surya, Jayani | Raksha | Pallavi | 24
Display List of Article | 8 | Surya, Jayani | Raksha | Pallavi | 24

## Sprint 5
Sprint 5 - 12/5/23 to 12/8/23
User Story | Assigned To | Story Points | Cumulative Hours
Code Inspection | ALL | 1 | 3
QA Testing | ALL | 1 | 3
Stress Testing | ALL | 1 | 3
UAT Testing | ALL | 1 | 3
User Manual | ALL | 1 | 3
Project Demo Preparation | ALL | 1 | 3